## Cost Estimate
North Bay Wheel Storage RIP & Adjacent Facilities Upgrade
Pricing Schedule
Note: This Section includes granular items and is encouraged to complete entirely. However, some of the items can be referred back to their Group Hierarchy such as- Electrical, Mechanical, Civil, Structural or track work.
ITEM | ITEM DESCRIPTION | ESTIMATED QUANTITY | UNIT | UNIT PRICE | Total
A | TOTAL ESTIMATED COSTS (DIRECT AND INDIRECT CONSTRUCTION COSTS - WITH CONTINGENCY) (C + D + E)
A | DIRECT CONSTRUCTION COSTS
GC | General Conditions
G1 | PROJECT INSURANCE & BONDING | 1 | LS
G2 | PROJECT STAFF | 1 | LS
G3 | SURVEYING & LOCATES | 1 | LS
G4 | GENERAL LABOUR | 1 | LS
G5 | PROJECT SITE OFFICE & SUPPLIES | 1 | LS
G6 | SANITARY FACILITIES | 1 | LS
G7 | COMMISSIONING | 1 | LS
G8 | PROJECT SIGNAGE | 1 | LS
G9 | TEMPORARY FENCING | 1 | LS
G10 | SAFETY SUPPLIES | 1 | LS
G11 | DISPOSAL BINS - GENERAL WASTE | 1 | LS
G12 | FINAL CLEANING | 1 | LS
G13 | CLOSEOUT DOCUMENTS | 1 | LS
1 | Construction Works |  |  | niveau 1
1.1 | Civil and Earthworks |  |  | niveau 2
1.1.1 | Preparatory works |  |  | niveau 3
1.1.1.001 | Clearing and grubbing | 3938 | m2
1.1.1.002 | Construction site organization and maintenance - Including construction and maintenance of access roads, circulation and storage areas | 1 | LS
1.1.2 | Demolition
1.1.2.001 | Asphalt removal and off site disposal | 1 | LS
1.1.2.002 | Retaining wall demolition and off site disposal | 1 | LS
1.1.3 | Earthworks
1.1.3.001 | Common excavation - Area: Slab on grade for the wheel storage area, including ramp | 498 | m3
1.1.3.002 | Common excavation - Area: Foundation for light posts | 16.8 | m3
1.1.3.003 | Common excavation - Area: Retaining wall (axle area fabric shelter) foundation | 46.2 | m3
1.1.3.005 | Common excavation - Area: Lunchroom, washroom and emergency shower building fundation | 187.51 | m3
1.1.3.006 | Common excavation - Area: Seacan storage container and shelter foundation | 268.1 | m3
1.1.3.007 | Common excavation - Area: RIP track platform | 118 | m3
1.1.3.008 | Common excavation - Area: Electrical and mechanical services buildings foundation | 216 | m3
1.1.3.009 | Common excavation - Area: Wheel storage ramp access pathway and area around lunchroom | 48 | m3
1.1.4 | Water Service
1.1.4.001 | 50 mm HDPE Pipes - DN50 HDPE, F 714, PE, ASTM D3350 PE4710 CL445574C, DR 7.3 | 13 | l.m.
1.1.5 | Sanitary sewer
1.1.5.001 | 200 mm PVC Pre-Insulated Sanitary Pipes (75mm Thick Insulation R7.14) | 118 | l.m.
1.1.5.002 | 200 mm PVC Non-Insulated Sanitary Pipes | 22 | l.m.
1.1.6 | Stormwater sewer
1.1.6.001 | 300 mm PVC Non-Insulated Storm Pipes | 50 | l.m.
1.1.6.002 | 200 mm PVC Pre-Insulated Storm Pipes (75mm Thick Insulation R7.14) | 43 | l.m.
1.1.6.003 | 100 mm PVC Pre-Insulated Condensate Pipe (50mm Thick Insulation R7.14) | 80 | l.m.
1.1.6.004 | Prefabricated trench drain - ACO S100K or equivalent | 240 | l.m.
1.1.6.005 | Prefabricated trench drain - ACO S200K or equivalent | 20 | l.m.
1.1.6.006 | Catch basin - ACO SK1-621D or equivalent | 20 | ea.
1.1.6.007 | Sanitary manhole - OPSD 701.030 1200mm dia. insulated - Including frame and cover | 4 | ea.
1.1.6.008 | Catch basin - OPSD 705.010 600x600mm insulated - Including frame and cover | 3 | ea.
1.1.6.009 | Relocation of existing concrete catch basin CCB-1 | 1 | ea.
1.1.6.010 | Frame and grate only for all existing catch basins - OPSD 400.010 | 6 | ea.
1.1.7 | Trenches and conduits for other utilities
1.1.7.001 | Cast in place electrical duck bank with 4 conduits | 225 | l.m.
1.1.8 | Erosion and sediment control
1.1.8.001 | Silt fence | 550 | l.m.
1.1.8.002 | Inlet protection for sanitary sewer network - FILTREXX SOXX system or equivalent | 6 | ea.
1.1.9 | Install Labor |  | LS
1.2 | Mechanical
1.2.1 | Demolition
1.2.1.001 | Demolition and off site disposal of existing compressed air network | 997 | l.m.
1.2.2 | Compressed air network
1.2.2.001 | Compressed air generating system | 1 | LS
1.2.2.002 | 50mm Carbon Steel Pipe - DN50 Pipe NPS, S-XS, B36.10M, MTE, A 106 Gr. B Seamless | 40 | l.m.
1.2.2.003 | 50mm HDPE Pipe - DN50 HDPE, F 714, PE, ASTM D3350 PE4710 CL445574C, DR 7.3 | 915 | l.m.
1.2.2.004 | 50mm HDPE Pipe - DN50 HDPE, F 714, PE, ASTM D3350 PE4710 CL445574C, DR 7.3 | 22 | l.m.
1.2.2.005 | Utility post compressed air outlet | 19 | ea.
1.2.3 | Install Labor |  | LS
1.3 | Electrical
1.3.1 | Demolition
1.3.1.001 | Demolition of existing 4160V overhead power lines including overhead switch and accessories | 1 | LS
1.3.1.002 | Demolition of existing 4160V overhead cable installed on wheel shop roof (3x¤2/0AWG, 5KV) | 100 | l.m.
1.3.1.003 | Demolition of existing electrical shack including electrical devices/conduits/cables inside | 1 | LS
1.3.1.004 | Demolition of miscellaneous elements | 1 | LS
1.3.1.005 | Demolition of existing three pole-mounted lighting fixtures and cables | 3 | set
1.3.2 | Electrical cable alignment
1.3.2.001 | 2/0-3C HL TECK90 BC XLPE INS 90MIL SHLD SIA ORG JKT CSA FT45KV C22.2 | 345 | l.m.
1.3.2.002 | 500-4C TECK 90 BC 1KV XLPE INS 1 #3 GRD SIA BLK PVC JKT FT4 CSA | 57.5 | l.m.
1.3.2.003 | NEW 150A fuse for "Existing 4160V switchgear" | 1 | set
1.3.2.004 | 4160-480/277V 750kVA transformer including 4160V load interrupter | 1 | ea.
1.3.2.005 | 480V 1200A Switchboard (2 sections) | 1 | ea.
1.3.2.006 | 480V Distribution Panel boards | 5 | ea.
1.3.2.007 | 208V/240V Distribution Panel boards | 6 | ea.
1.3.2.008 | 480V manual transfer switch 300A | 1 | ea.
1.3.2.009 | 480V 225A breaker | 1 | ea.
1.3.2.010 | 480-208/120V 75kVA transformer | 1 | ea.
1.3.2.011 | 480-208/120V 30kVA transformer | 2 | ea.
1.3.2.012 | 480V disconnect switch 100 A | 1 | ea.
1.3.2.013 | 2/0-3C HL TECK90 BC; CROUSE HINDS TECK200-13S, 2.0" STEEL TECK CONNECTOR C/W LOCK NUT RANGE, 1.900-2.187" CSA | 6 | ea.
1.3.2.014 | 500-4C TECK 90 BC 1KV;CROUSE HINDS TECK300-19S, WATERTIGHT CONN'OR 3"HUB TECK90/ACWU, CABLE OD2.79"-3.06" CSA | 2 | ea.
1.3.2.015 | Terminations: 2/0-3C HL TECK90 BC | 18 | ea.
1.3.2.016 | Terminations: 500-4C TECK 90 BC 1KV | 8 | ea.
1.3.2.017 | Point to Point/ Meger cable testing | 403 | l.m.
1.3.2.018 | Cable tagging | 403 | l.m.
1.3.2.019 | Wire markers | 403 | l.m.
1.3.2.020 | Misc. hardware | 1 | lot
1.3.3 | Yard lighting
1.3.3.001 | Pole lighting fixtures and accessories | 22 | ea.
1.3.3.002 | Wall pack lighting fixtures DSXW1 LED P6 40K T3M | 6 | ea.
1.3.3.003 | Mounting of existing pole lighting fixture (DSX2 LED P2 40K 70 CRI T4M_3 - double) on new pole | 1 | ea.
1.3.3.004 | New lighting pole - 18ft H 4inch square | 10 | ea.
1.3.3.005 | Electrical manhole (1200mmLx1650mmWx2100mmD) | 4 | ea.
1.3.3.006 | Uninstallation and reinstallation of existing wooden lightning pole and pole lighting fixture | 2 | ea.
1.3.4 | Utility posts
1.3.4.001 | Welding plug including disconnect switch 60 A, (c/w 3R enclosure for exterior weld plugs) | 19 | ea.
1.3.4.002 | GFCI protection 20A, 20A/120V Receptacles complete with cover | 19 | ea.
1.3.5 | Cables, conduits and grounding
1.3.5.001 | 250-3C TECK 90 BC 1KV XLPE INS 1 #4 GRD SIA BLK PVC JKT FT4 CSA | 224.25 | l.m.
1.3.5.002 | 4/0-4C TECK 90 BC 1KV XLPE INS 1 #4 GRD SIA BLK PVC JKT FT4 CSA | 172.5 | l.m.
1.3.5.003 | 4/0-3C TECK 90 BC 1KV XLPE INS 1 #4 GRD SIA BLK PVC JKT FT4 CSA | 11.5 | l.m.
1.3.5.004 | 3/0-3C TECK 90 BC 1KV XLPE INS 1 #4 GRD SIA BLK PVC JKT FT4 CSA | 11.5 | l.m.
1.3.5.005 | 1/0-4C TECK 90 BC 1KV XLPE INS 1 #6 GRD SIA BLK PVC JKT FT4 CSA | 103.5 | l.m.
1.3.5.006 | 1-3C TECK 90 BC 1KV XLPE INS 1 #6 GRD SIA BLK PVC JKT FT4 CSA | 23 | l.m.
1.3.5.007 | 4-3C TECK 90 BC 1KV XLPE INS 1 #8 GRD SIA BLK PVC JKT FT4 CSA | 11.5 | l.m.
1.3.5.008 | 3-4C TECK 90 BC 1KV XLPE INS 1 #6 GRD SIA BLK PVC JKT FT4 CSA | 34.5 | l.m.
1.3.5.009 | 3-3C TECK 90 BC 1KV XLPE INS 1 #6 GRD SIA BLK PVC JKT FT4 CSA | 764.75 | l.m.
1.3.5.010 | 10-3C TECK 90 BC 1KV XLPE INS 1 #12 GRD SIA BLK | 172.5 | l.m.
1.3.5.011 | 6-1C 7 STR BC RW90 XLPE INS 90C 600V BLK CSA C22.2 NO.38 | 2875 | l.m.
1.3.5.012 | 12-1C 7 STR BC RW90 XLPE INS 90C 600V BLK CSA C22.2 NO.38 | 5175 | l.m.
1.3.5.013 | 250-3C TECK 90 BC 1KV; CROUSE HINDS TECK200-14S, 2.0" STEEL TECK CONNECTOR C/W LOCK NUT OD: 2.100-2.375 CSA | 4 | ea.
1.3.5.014 | 4/0-4C TECK 90 BC 1KV; CROUSE HINDS TECK200-14S, 2.0" STEEL TECK CONNECTOR C/W LOCK NUT OD: 2.100-2.375 CSA | 4 | ea.
1.3.5.015 | 4/0-3C TECK 90 BC 1KV; CROUSE HINDS TECK200-13S, 2.0" STEEL TECK CONNECTOR C/W LOCK NUT RANGE, 1.900-2.187" CSA | 2 | ea.
1.3.5.016 | 3/0-3C TECK 90 BC 1KV; CROUSE HINDS TECK150-11S, 1.5" STEEL TECK CONNECTOR C/W LOCK NUT RANGE: 1.700"-1.965" CSA | 2 | ea.
1.3.5.017 | 1/0-4C TECK 90 BC 1KV ; CROUSE HINDS TECK150-11S, 1.5" STEEL TECK CONNECTOR C/W LOCK NUT RANGE: 1.700"-1.965" CSA | 2 | ea.
1.3.5.018 | 1-3C TECK 90 BC 1KV; CROUSE HINDS TECK100-7S, 1" STEEL TECK CONNECTOR C/W LOCK NUT RANGE: 1.187"-1.375" CSA | 2 | ea.
1.3.5.019 | 4-3C TECK 90 BC 1KV XLPE INS 1 #8 GRD SIA BLK PVC JKT FT4 CSA | 2 | ea.
1.3.5.020 | 3-4C TECK 90 BC 1KV; CROUSE HINDS TECK125-8S, 1.25" STEEL TECK CONNECTOR C/W LOCK NUT RANGE: 1.350"-1.625" CSA | 10 | ea.
1.3.5.021 | 3-3C TECK 90 BC 1KV; CROUSE HINDS TECK100-7S, 1" STEEL TECK CONNECTOR C/W LOCK NUT RANGE: 1.187"-1.375" CSA | 8 | ea.
1.3.5.022 | 10-3C TECK 90 BC 1KV; CROUSE HINDS TECK050-4S, 1/2" STEEL TECK CONNECTOR C/W LOCK NUT RANGE: 825-.985" CSA | 2 | ea.
1.3.5.023 | Point to Point/ Meger cable and wire testing | 9583 | l.m.
1.3.5.024 | Cable and wire tagging | 9583 | l.m.
1.3.5.025 | Cablre and wire markers | 9583 | l.m.
1.3.5.026 | Misc. hardware | 1 | lot
1.3.6 | Grounding
1.3.6.001 | Ground bus Strips complete with a cross section of 25 mm x 6 mm | 31.15 | l.m.
1.3.6.002 | 4/0-1C SOFT DRAWN 19 STR BARE COPPER | 81.15 | l.m.
1.3.6.003 | 2/0-1C SOFT DRAWN 19 STR BARE COPPER CLASS B | 201.15 | l.m.
1.3.6.004 | 6-1C SOFT DRAWN 7 STR BARE COPPER | 21.15 | l.m.
1.3.6.005 | Ground rod 19 mm x 3048 mm | 16 | ea.
1.3.6.006 | Ground rod with inspection well | 3 | ea.
1.3.6.007 | Equipment bonding connections | 1 | LS
1.3.6.008 | Lighting as per drawing schedules | 1 | LS
1.3.6.009 | Ground Bond connectors | 1 | LS
1.3.6.010 | Equipment and Cable Tagging, Labelling | 1 | LS
1.3.6.011 | Equipment testing, cable testing, megering, test reports | 1 | LS
1.3.6.012 | Misc. Components | 1 | LS
1.3.7 | Install Labor |  | LS
1.4 | Structure
1.4.1 | Demolition
1.4.1.001 | Concrete demolition and off site disposal - Area: Wheel storage area | 176 | m3
1.4.1.002 | Concrete demolition and off site disposal - Area: Lunchroom, washroom and emergency shower building fundation | 33.09 | m3
1.4.1.003 | Concrete demolition and off site disposal - Area: Seacan storage container and shelter foundation | 47.35 | m3
1.4.1.004 | Concrete demolition and off site disposal - Area: RIP track platform | 356 | m3
1.4.2 | Concrete works
1.4.2.001 | Cast in place concrete - Slab on grade for the wheel storage area | 272 | m3
1.4.2.002 | Cast in place concrete - Foundation for light posts | 19 | m3
1.4.2.003 | Cast in place concrete - Retaining wall (axle area fabric shelter) foundation | 59 | m3
1.4.2.004 | Cast in place concrete - Ramp (concrete) | 11 | m3
1.4.2.005 | Cast in place concrete - Lunchroom, washroom and emergency shower building foundation | 19.3 | m3
1.4.2.006 | Cast in place concrete - Seacan storage container and shelter foundation. | 38.5 | m3
1.4.2.007 | Cast in place concrete - RIP track area platform | 357 | m3
1.4.2.008 | Cast in place concrete - Electrical and mechanical services buildings foundation | 19.5 | m3
1.4.2.009 | Cast in place concrete - Wheel storage ramp access pathway and area around lunchroom | 64 | m3
1.4.3 | Other structures
1.4.3.001 | Lock-Block (Retaining Wall) (750mmx750mmx1500mm) | 61 | ea.
1.4.3.002 | Lock-Block (Under the Axle Storage Shelter) (750mmx750mmx1500mm) | 22 | ea.
1.4.3.003 | 1.455 m H 500mm square New Utility post as shown on DWG-230-270-0015 | 19 | ea.
1.4.4 | Install Labor |  | LS
1.5 | Architecture
1.5.1 | Demolition
1.5.1.001 | RIP shack building demolition and Including off site disposal | 1 | LS
1.5.1.002 | Electrical shack building demolition and Including off site disposal | 1 | LS
1.5.1.003 | Existing utility post demolition and Including off site disposal | 16 | ea.
1.5.2 | Buildings
1.5.2.001 | Lunchroom, Washroom, and Emergency Shower/Eyewash Building (Pre-fabricated modular building, 12.8 m x 3.6 m) | 1 | LS
1.5.2.002 | Accessible RAMP for the Lunchroom | 1 | ea.
1.5.2.003 | Electrical and Mechanical Services Building (Pre-fabricated modular building, 17.6 m x 3.6 m) | 1 | LS
1.5.3 | Storages
1.5.3.001 | 2 Seacan Container 40 ft (incl. door and window) with Fabric shelter (11m width x12.19m length x 5.5m height) as shown on DWG- 290-270-0003 | 1 | LS
1.5.3.002 | Fabric shelter for axle storage area (8.93m width x 16.5m length x 6m height) | 1 | LS
1.5.4 | Install Labor |  | LS
2 | Rail Works
2.1 | Track alignment
2.1.1 | Preparatory works
2.1.1.001 | Concrete Embedded Track Removal | 535 | trk.m
2.1.1.002 | Ballast Track Removal - Including excavation 6-inch Ballast below Tie, Rail Tie and OTM Removal | 34 | trk.m
2.1.1.003 | Ballast Track Removal - Including excavation 15 inch below Tie, Rail Salvage for Reuse, 50% Ties OTM Ballast for Reuse, as shown on DWG-260-0001 | 352 | trk.m
2.1.2 | Track works
2.1.2.001 | Installation of concrete embeded track - 115lbs (all track material to be provided by GC) | 482 | trk.m
2.1.2.004 | Installation of ballast track - 90 lbs (all track material to be provided by GC, along with the ballast) | 375 | trk.m
2.1.3 | Bumping posts
2.1.3.001 | Bumping Post - New Installation on Concrete Embedded Track: Hayes Type WG or HD (or equivalent) | 2 | ea.
2.1.3.002 | Bumping Post - New Installation on Ballast Track: Hayes Type WG or HD (or equivalent) | 1 | ea.
2.1.3.003 | Bumping Post - Existing Removal, Salvage for Re-installation on Ballast Track | 1 | ea.
2.1.4 | Install Labor |  | LS
Cash Allowance | Excess Soil Management |  | lot. |  | 100000
| Allowance for replacing the underground storm & Sewer lines connected to the Cath basins listed on the drawings No# (H375313-1000-220-272-0004 H375313-1000-220-258-0001) Civil Package. |  | LS |  | 350000
Total Before Tax
HARMONIZED SALES TAX (HST) @ 13%
TOTAL w HST
Note on D31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hypothèse: Environ 150 m2
Note on D32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Hypothèse: Environ 100 m
Note on C190: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Everything

## Domestic Supply Chain
Domestic Supply Chain Plan
Proponents are requested to refer to Appendix D – Schedule of Prices within the RFP for detailed instructions on completing the table below. A completed example is provided below and has also been included within the RFP for reference. Proponents must follow the example provided and complete the table below accordingly. Please complete only the table corresponding to the package(s) for which you are submitting a proposal. Completion of this table is mandatory. Failure to complete the applicable table may result in disqualification.
Example of Domestic Supply Chain Table
Item Description | Origin | Dollar Value (CAD)
(Ontario, Canada, elsewhere)
Example: Concrete | Ontario | 50000
Example: Steel | Canada | 30000
Example: Fixtures | Other | 10000
Package 2 - North Bay, ON
| Item Description | Origin | Dollar Value (CAD)
(Ontario, Canada, elsewhere)
Goods
Asphalt
Concrete
Reinforcement Bar
Electrical Supply & Equipment
Mechanical Supply & Equipment
HVAC Equipment
Modular Building
Rail Tracks
Sea Containers
Steel
Services
General Labor
Electrician
Project Staff
Commissioning
Inspection

## Pricing for Change Orders
PRICING FOR CHANGE ORDERS / CHANGE DIRECTIVES:
Please quote overhead and profit percentage based on the following project cost ranges:
Project Costs | Overhead % | Profit %
$0 up to $9,999
$10,000 up to $49,999
$50,000 up to $99,999
$100,000 up to 149,999
$150,000 up to $200,000
$200,000 and higher
Please note that these project cost ranges apply to the aggregate price of all change orders and not on a per change order basis. Any OH&P applied shall be calculated against the subtotal of the applicable change order only. ONTC reserves the right to not accept the percentage values provided in the table above and any future change order markups will be reviewed and agreed upon by ONTC and contractor.
Please provide the hourly rate of pay for the following (add an additional page for any Positions not listed below):
Position | Hourly Rate
Project Manager
Estimator
Scheduler
Civil Engineering
Site Supervisor
Carpenter
Electrician
Mechanical Engineer
Mechanical HVAC Contractor Technician
Masonry/Concrete Labour
Concrete Truck Operator
Crane Operator
Welder
General Labour

## Schedule of Progress Payments
Schedule of Progress Payments
Please provide your schedule of progress payments below identifying all payment milestones, associated deliverables, and corresponding payment amounts or percentages.